## Summary
Off Grid iOS ↔ macOS Sync Manual Gate
Release scope: iOS and macOS only. Update Status and Evidence as physical testing progresses.
Metric | Value | Area | Total | Verified
Total test cases | 108 | Pairing & identity | 9 | 0
Verified by user | 8 | Discovery & routes | 9 | 0
Not started | 99 | Membership | 7 | 0
In progress | 0 | Chats & messages | 10 | 4
Blocked - coding | 0 | Projects | 5 | 1
Completion | 7.407% | Knowledge base | 8 | 1
|  | Clipboard | 5 | 0
|  | Settings & models | 5 | 0
|  | Files | 26 | 1
|  | Files UI | 8 | 0
|  | Activity & notifications | 7 | 0
|  | Persistence & conflicts | 5 | 0
|  | Desktop capture | 3 | 1
|  | Navigation | 1 | 0
Current known scope notes
Verified so far | iOS → macOS: chat/project sync, messages, thinking, tool results, generated tool artifacts, knowledge document sync and generic file sync. macOS Replay capture toggle ↔ menu-bar state is also verified.
In progress | Shared ambient-directory source is consumed by both hosts. Desktop Pro is d1b6f9d/7c126fe; Mobile Pro is 1665fc43/98be179c and current iOS is physically installed. Manual verification remains.
Coding backlog | No known coding blocker remains in this matrix. Cmd+[ / Cmd+] history is implemented and is ready for manual verification.
Deferred | The five-device hard cap requires a physical multi-device setup.

## Test Matrix
Comprehensive iOS ↔ macOS Sync Test Matrix
Use one row per user journey. Record screenshots, timestamps or bug IDs in Evidence / Bug.
Status options: Not Started, In Progress, Verified by User, Failed, Blocked - Coding, Deferred, N/A.
ID | Area | Test case | Direction | Source | Destination | Priority | Scope | Status | Preconditions | Manual steps | Expected result | Evidence / Bug | Notes
SYNC-IOSMAC-001 | Pairing & identity | Pairing code persists across an iOS app restart | iOS local | iOS | iOS | P0 | Pro | Not Started | Pairing code is visible. | Record the code; terminate and relaunch the iOS app. | The same code is displayed until the user explicitly rotates it.
SYNC-IOSMAC-002 | Pairing & identity | Pairing code persists across a macOS app restart | macOS local | macOS | macOS | P0 | Pro | Not Started | Pairing code is visible. | Record the code; quit and relaunch Off Grid AI Desktop. | The same code is displayed until the user explicitly rotates it.
SYNC-IOSMAC-003 | Pairing & identity | Rotating the pairing code invalidates the previous code | Both | Either | Peer | P0 | Pro | Not Started | Devices are unpaired or a disposable pairing is available. | Rotate the code; attempt pairing with the old code; then use the new code. | The old code fails with canonical feedback; the new code pairs successfully.
SYNC-IOSMAC-004 | Pairing & identity | iOS initiates pairing and shows the complete lifecycle | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Devices are discoverable and not paired. | Start pairing on iOS; observe connecting, confirmation, durable success. | Both devices show one truthful lifecycle and become paired only after durable persistence.
SYNC-IOSMAC-005 | Pairing & identity | macOS initiates pairing and shows the complete lifecycle | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Devices are discoverable and not paired. | Start pairing on macOS; observe connecting, confirmation, durable success. | Both devices show one truthful lifecycle and become paired only after durable persistence.
SYNC-IOSMAC-006 | Pairing & identity | Wrong pairing code is visible on both devices | Both | Either | Peer | P0 | Pro | Not Started | Devices are discoverable and not paired. | Enter an incorrect code and wait for the attempt to finish. | Neither device is paired; both receive canonical failure feedback and Retry.
SYNC-IOSMAC-007 | Pairing & identity | Cancel and Retry do not resurrect an old pairing attempt | Both | Either | Peer | P1 | Pro | Not Started | A pairing attempt is in progress. | Cancel; retry; complete pairing. | Only the current attempt remains visible; the old failure does not return.
SYNC-IOSMAC-008 | Pairing & identity | Rename iOS device and preserve the name | iOS → macOS | iOS | macOS | P1 | Pro | Not Started | Devices are paired. | Rename iOS; reconnect; restart both apps. | The new name persists locally and is shown on macOS.
SYNC-IOSMAC-009 | Pairing & identity | Rename macOS device and preserve the name | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | Devices are paired. | Rename macOS; reconnect; restart both apps. | The new name persists locally and is shown on iOS.
SYNC-IOSMAC-010 | Discovery & routes | Connect over LAN and show the authenticated route | Both | Either | Peer | P0 | Pro | Not Started | Both devices are on the same local network. | Rescan and connect. | Both devices show Connected · LAN; no stale Nearby or transport error is visible.
SYNC-IOSMAC-011 | Discovery & routes | Connect over Nearby with LAN unavailable | Both | Either | Peer | P0 | Pro | Not Started | Devices are adjacent; disable Wi-Fi/LAN without unpairing. | Rescan and connect over Nearby. | Both devices show Connected · Nearby and sync traffic still works.
SYNC-IOSMAC-012 | Discovery & routes | Prefer LAN over Nearby when both routes are available | Both | Either | Peer | P0 | Pro | Not Started | LAN and Nearby are both factually available. | Disconnect and reconnect. | The authenticated route is LAN; a late Nearby attempt is closed without a stale error.
SYNC-IOSMAC-013 | Discovery & routes | Fall back from LAN to Nearby | Both | Either | Peer | P0 | Pro | Not Started | Devices are paired and connected over LAN. | Remove LAN availability; reconnect without re-pairing. | Connection succeeds over Nearby and the route label changes factually.
SYNC-IOSMAC-014 | Discovery & routes | Return from Nearby to LAN after LAN becomes available | Both | Either | Peer | P1 | Pro | Not Started | Devices are connected over Nearby. | Restore LAN; disconnect and reconnect. | The next connection uses LAN.
SYNC-IOSMAC-015 | Discovery & routes | Rescan preserves discovery subscriptions | Both | Either | Peer | P0 | Pro | Not Started | Devices are running and discoverable. | Rescan repeatedly; then make the peer disappear and reappear. | Scanning state is truthful and the peer can still be found after every rescan.
SYNC-IOSMAC-016 | Discovery & routes | Heartbeat clears a genuinely dead connection | Both | Either | Peer | P0 | Pro | Not Started | Devices are connected. | Make one device unreachable without pressing Disconnect; wait for liveness timeout. | Connected changes to Offline; stale Connected state is not retained.
SYNC-IOSMAC-017 | Discovery & routes | Restart both apps and reconnect without pairing again | Both | Either | Peer | P0 | Pro | Not Started | Devices are paired. | Restart both apps and allow discovery to settle. | Saved membership remains and the devices reconnect without a new code.
SYNC-IOSMAC-018 | Discovery & routes | Discoverability health reports factual partial failures | Both | Either | Peer | P1 | Pro | Not Started | At least one route can be intentionally made unavailable. | Disable one route while leaving the other healthy. | UI distinguishes Discoverable, Partially available and Not discoverable using factual route health.
SYNC-IOSMAC-019 | Membership | Evict iOS from macOS and converge bilaterally | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Devices are paired and online. | Evict iOS from macOS and confirm. | The local slot releases immediately; both devices remove the membership after authenticated acknowledgement.
SYNC-IOSMAC-020 | Membership | Evict macOS from iOS and converge bilaterally | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Devices are paired and online. | Evict macOS from iOS and confirm. | The local slot releases immediately; both devices remove the membership after authenticated acknowledgement.
SYNC-IOSMAC-021 | Membership | Offline eviction survives restart and completes later | Both | Either | Peer | P0 | Pro | Not Started | Peer is paired but offline. | Evict; restart the initiator; bring the peer back. | Pending eviction survives restart and completes after authenticated rediscovery.
SYNC-IOSMAC-022 | Membership | Dismiss a failed eviction without abandoning revocation | Both | Either | Peer | P1 | Pro | Not Started | An offline eviction is in failed/pending delivery. | Dismiss the failed card; reconnect the peer. | The card hides, but durable revocation continues and eventually converges.
SYNC-IOSMAC-023 | Membership | Explicit re-pair supersedes a stale pending eviction | Both | Either | Peer | P0 | Pro | Not Started | A legacy or unacknowledgeable pending eviction exists. | Use Pair again and complete pairing. | A new membership generation is durable and the old pending revocation is removed.
SYNC-IOSMAC-024 | Membership | Mesh slot counts agree across both devices | Both | Either | Peer | P1 | Pro | Not Started | At least one remote membership exists. | Pair, evict and restart while comparing counts. | Both screens report 1 local + saved peers, with a maximum of 5.
SYNC-IOSMAC-025 | Membership | Five-device membership cap is enforced | Both | Either | Peer | P2 | Pro | Deferred | Five physical devices or a supported physical-device lab are available. | Fill all five slots and attempt one more pairing. | The sixth device cannot be added; UI explains the full mesh and allows eviction. |  | Deferred until enough physical devices are available.
SYNC-IOSMAC-026 | Chats & messages | Create and sync a chat | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | Devices are paired and connected. | Create a chat and send a message on iOS. | The chat and message appear on macOS without restart.
SYNC-IOSMAC-027 | Chats & messages | Create and sync a chat | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Devices are paired and connected. | Create a chat and send a message on macOS. | The chat and message appear on iOS without restart.
SYNC-IOSMAC-028 | Chats & messages | Preserve reasoning/thinking structure | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | A reasoning-capable response exists. | Sync the response. | Answer and thinking render as the same structured turn on macOS.
SYNC-IOSMAC-029 | Chats & messages | Preserve reasoning/thinking structure | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | A reasoning-capable response exists. | Sync the response. | Answer and thinking render as the same structured turn on iOS.
SYNC-IOSMAC-030 | Chats & messages | Preserve tool calls and tool results | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | A completed tool call/result exists. | Sync the turn. | Tool identity, result, status and ordering render correctly without rerunning the tool.
SYNC-IOSMAC-031 | Chats & messages | Preserve tool calls and tool results | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | A completed tool call/result exists. | Sync the turn. | Tool identity, result, status and ordering render correctly without rerunning the tool.
SYNC-IOSMAC-032 | Chats & messages | Preserve generated tool artifacts | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | A portable generated artifact exists on a message. | Sync the turn. | The artifact is attached to the correct message and opens on macOS.
SYNC-IOSMAC-033 | Chats & messages | Preserve generated tool artifacts | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | A portable generated artifact exists on a message. | Sync the turn. | The artifact is attached to the correct message and opens on iOS.
SYNC-IOSMAC-034 | Chats & messages | Delete a chat without resurrection | Both | Either | Peer | P1 | Pro | Not Started | The chat exists on both devices. | Delete on one device; reconnect/restart both. | The chat remains deleted and is not recreated by stale state.
SYNC-IOSMAC-035 | Chats & messages | Record immutable origin provenance | Both | Either | Peer | P1 | Pro | Not Started | New chats/messages are created on both devices. | Inspect the synced records or visible attribution where exposed. | Each record keeps its original device ID/name through edits and restarts.
SYNC-IOSMAC-036 | Projects | Create and sync a project | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | Devices are paired and connected. | Create or edit a project on iOS. | Project identity and settings appear on macOS.
SYNC-IOSMAC-037 | Projects | Create and sync a project | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Devices are paired and connected. | Create or edit a project on macOS. | Project identity and settings appear on iOS.
SYNC-IOSMAC-038 | Projects | Assign a chat to an already-open project screen | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | The project detail screen is open on macOS. | Assign a synced chat to the project on iOS. | The open macOS project screen updates immediately without navigation or restart.
SYNC-IOSMAC-039 | Projects | Assign a chat to an already-open project screen | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | The project detail screen is open on iOS. | Assign a synced chat to the project on macOS. | The open iOS project screen updates immediately.
SYNC-IOSMAC-040 | Projects | Delete a project without resurrecting it | Both | Either | Peer | P1 | Pro | Not Started | The project exists on both devices. | Delete on one device; reconnect/restart. | The project and its assignment state converge without deleting unrelated local data.
SYNC-IOSMAC-041 | Knowledge base | Add and index a knowledge document | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | A synced project exists. | Add a supported document on iOS. | macOS receives exact source bytes, indexes under the same project and shows it without restart.
SYNC-IOSMAC-042 | Knowledge base | Add and index a knowledge document | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | A synced project exists. | Add a supported document on macOS. | iOS receives exact source bytes, indexes under the same project and shows it without restart.
SYNC-IOSMAC-043 | Knowledge base | Search a very short knowledge document | Both | Either | Peer | P0 | Pro | Not Started | A text file containing only a few non-empty characters is available. | Add, sync and ask the receiving chat for its exact content. | The short document produces an indexed chunk and the answer uses its real content.
SYNC-IOSMAC-044 | Knowledge base | Toggle knowledge-document enabled state | iOS → macOS | iOS | macOS | P1 | Pro | Not Started | The document exists on both devices. | Disable and re-enable on iOS. | macOS converges to the latest enabled state, including if changed during import.
SYNC-IOSMAC-045 | Knowledge base | Toggle knowledge-document enabled state | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | The document exists on both devices. | Disable and re-enable on macOS. | iOS converges to the latest enabled state.
SYNC-IOSMAC-046 | Knowledge base | Delete a knowledge document | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | The document exists on both devices. | Delete on iOS. | macOS removes only that document and does not rebroadcast or resurrect it.
SYNC-IOSMAC-047 | Knowledge base | Delete a knowledge document | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | The document exists on both devices. | Delete on macOS. | iOS removes only that document and does not rebroadcast or resurrect it.
SYNC-IOSMAC-048 | Knowledge base | Stage a document until its project arrives | Both | Either | Peer | P1 | Pro | Not Started | File/control delivery can precede project state. | Share a document before the receiving project has materialized. | The receiver retains it and imports after the project arrives; nothing is silently dropped.
SYNC-IOSMAC-049 | Clipboard | Sync copied text with immutable attribution | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Clipboard sync is enabled and devices are connected. | Copy unique text on iOS. | macOS shows one item with iOS origin and a valid Unix timestamp.
SYNC-IOSMAC-050 | Clipboard | Sync copied text with immutable attribution | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Clipboard sync is enabled and devices are connected. | Copy unique text on macOS. | iOS shows one item with macOS origin and a valid Unix timestamp.
SYNC-IOSMAC-051 | Clipboard | Suppress repeated delayed native echoes | Both | Either | Peer | P0 | Pro | Not Started | A remote clipboard item has just been written to the native clipboard. | Wait, return to the app and observe the same native value multiple times. | No outbound bounce occurs and the retained record keeps its remote provenance.
SYNC-IOSMAC-052 | Clipboard | Restore, delete and clear clipboard history safely | Both | Either | Peer | P1 | Pro | Not Started | Clipboard history contains local and remote items. | Restore a remote item; delete one item; clear history. | Restore does not rebroadcast; delete/clear update history and delayed echoes do not recreate items.
SYNC-IOSMAC-053 | Clipboard | Clipboard history and provenance survive restart | Both | Either | Peer | P1 | Pro | Not Started | Clipboard history contains attributed records. | Restart both apps. | Ordering and immutable origin remain correct.
SYNC-IOSMAC-054 | Settings & models | Sync model/inference settings | iOS → macOS | iOS | macOS | P1 | Pro | Not Started | A setting exists on both platforms. | Change the setting on iOS. | macOS updates without restart or an echo loop.
SYNC-IOSMAC-055 | Settings & models | Sync model/inference settings | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | A setting exists on both platforms. | Change the setting on macOS. | iOS updates without restart or an echo loop.
SYNC-IOSMAC-056 | Settings & models | Send a model package from macOS to iOS | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | A compatible model is installed on macOS and enough iOS storage is available. | Press Send model and choose the model. | Progress is visible; exact package bytes arrive; the model becomes usable on iOS.
SYNC-IOSMAC-057 | Settings & models | Reject an incompatible or oversized model package truthfully | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | A package that violates admission is available. | Attempt the transfer. | The receiver refuses before materialization and both sides show a useful failure.
SYNC-IOSMAC-058 | Settings & models | Resume an interrupted model transfer | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | A model transfer is active. | Interrupt connectivity; restore it; retry/resume. | Transfer resumes without duplicate completed activities or corrupt bytes.
SYNC-IOSMAC-059 | Files | Sync a generic file | iOS → macOS | iOS | macOS | P0 | Pro | Verified by User | Devices are connected. | Share a supported file from iOS. | macOS receives the exact file and materializes it in Synced Files.
SYNC-IOSMAC-060 | Files | Sync a generic file | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Devices are connected. | Share a supported file from macOS. | iOS receives the exact file and materializes it in Synced Files.
SYNC-IOSMAC-061 | Files | Explicit Share file works while automatic sharing is Off | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Automatic sharing is Off. | Use Share file on iOS and select macOS. | The chosen file is admitted and delivered once; automatic policy does not block explicit intent.
SYNC-IOSMAC-062 | Files | Explicit Share file works while automatic sharing is Off | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Automatic sharing is Off. | Use Share file on macOS and select iOS. | The chosen file is admitted and delivered once.
SYNC-IOSMAC-063 | Files | Screenshot policy Off sends nothing | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Screenshot sharing is Off for the destination. | Take a new screenshot. | No control, bytes, queue item or approval is created.
SYNC-IOSMAC-064 | Files | Screenshot policy Ask creates one approval | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Screenshot sharing is Ask for the destination. | Take a new screenshot. | One newest-first approval notification appears; no bytes leave until approval.
SYNC-IOSMAC-065 | Files | Screenshot policy Auto shares in the background | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Screenshot sharing is Auto for the destination. | Take a new screenshot and continue using the app. | Transfer runs in the background; both sides receive factual completion feedback.
SYNC-IOSMAC-066 | Files | Screenshot policy Off sends nothing | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Screenshot sharing is Off for the destination. | Take a new screenshot. | No control, bytes, queue item or approval is created.
SYNC-IOSMAC-067 | Files | Screenshot policy Ask creates one approval | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Screenshot sharing is Ask for the destination. | Take a new screenshot. | One newest-first approval notification appears; no bytes leave until approval.
SYNC-IOSMAC-068 | Files | Screenshot policy Auto shares in the background | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Screenshot sharing is Auto for the destination. | Take a new screenshot and continue using the app. | Transfer runs in the background; both sides receive factual completion feedback.
SYNC-IOSMAC-069 | Files | Approve an Ask item | Both | Either | Peer | P0 | Pro | Not Started | A pending Ask approval exists. | Approve the item from Notifications. | Exactly that control and file are delivered to the named destination.
SYNC-IOSMAC-070 | Files | Reject an Ask item | Both | Either | Peer | P0 | Pro | Not Started | A pending Ask approval exists. | Reject the item. | Neither control nor bytes are sent; the result notification is truthful.
SYNC-IOSMAC-071 | Files | Filter automatic sharing by document/image/file kind | Both | Either | Peer | P0 | Pro | Not Started | Ask or Auto is enabled with a restricted type selection. | Create matching and non-matching files. | Only supported, selected kinds are admitted; hidden/partial/unsupported files are ignored.
SYNC-IOSMAC-072 | Files | Choose one destination without affecting other paired devices | Both | Either | Peer | P1 | Pro | Not Started | More than one paired destination is available. | Set a per-device rule or explicitly select one destination. | Only the selected destination receives the item.
SYNC-IOSMAC-073 | Files | Queue while offline and re-evaluate current policy on reconnect | Both | Either | Peer | P0 | Pro | Not Started | Queue while offline is enabled and peer is offline. | Create a file; change its policy; reconnect. | The item remains visible and is re-evaluated using the latest policy before sending.
SYNC-IOSMAC-074 | Files | Resume an interrupted file transfer | Both | Either | Peer | P0 | Pro | Not Started | A file transfer is active. | Interrupt connectivity and restore it. | Transfer resumes from verified progress and completes with the correct checksum.
SYNC-IOSMAC-075 | Files | Retry only one failed file | Both | Either | Peer | P0 | Pro | Not Started | At least two activities exist and one has failed. | Press Retry on the failed item. | Only the selected logical activity retries; no duplicate rows are created.
SYNC-IOSMAC-076 | Files | Repair bytes received before control | Both | Either | Peer | P1 | Pro | Not Started | Transport can deliver bytes before StateSync control. | Interrupt/reorder delivery and reconnect. | Bytes stay staged; missing control is requested; file materializes only after governed control.
SYNC-IOSMAC-077 | Files | Repair control received before bytes | Both | Either | Peer | P1 | Pro | Not Started | StateSync control exists but local bytes are missing. | Reconnect the source. | Missing bytes are requested and the file materializes once, without duplicate metadata.
SYNC-IOSMAC-078 | Files | Automatic Downloads folder source on macOS | macOS → iOS | macOS | iOS | P0 | Pro | Not Started | Shared ambient-directory owner and Desktop Pro adapter are landed. | Choose Downloads; add a completed file; test foreground/manual/watch scans. | Shared lifecycle dedupes and delivers supported completed files without touching partial/hidden files. |  | Shared 796f5ed/f335106/55b1d1a; Desktop Pro d1b6f9d/7c126fe.
SYNC-IOSMAC-079 | Files | Automatic Files-folder source on iOS | iOS → macOS | iOS | macOS | P0 | Pro | Not Started | Shared ambient-directory owner and the current physical Mobile adapter are installed. | Choose a Files folder; add a completed file; foreground or use Scan now. | Shared lifecycle admits completed supported files and delivers them once. |  | Shared 796f5ed/f335106/55b1d1a; Mobile Pro 1665fc43/98be179c; Mobile core a9fbbb6f.
SYNC-IOSMAC-080 | Files | Generated media record and bytes materialize in Gallery | iOS → macOS | iOS | macOS | P1 | Pro | Not Started | Generated-media sharing is enabled. | Generate media on iOS and sync it. | Metadata and exact bytes arrive; Open routes to Gallery.
SYNC-IOSMAC-081 | Files | Generated media record and bytes materialize in Gallery | macOS → iOS | macOS | iOS | P1 | Pro | Not Started | Generated-media sharing is enabled. | Generate media on macOS and sync it. | Metadata and exact bytes arrive; Open routes to Gallery.
SYNC-IOSMAC-082 | Files | Message image attachment materializes in its chat | Both | Either | Peer | P1 | Pro | Not Started | The owning conversation and message have stable synced IDs. | Attach a supported image; sync in both directions. | Attachment waits for its message if necessary, appears once and opens from the owning chat.
SYNC-IOSMAC-083 | Files | Message document attachment materializes in its chat | Both | Either | Peer | P1 | Pro | Not Started | The owning conversation and message have stable synced IDs. | Attach a supported document; sync in both directions. | Attachment waits for its message if necessary, appears once and opens from the owning chat.
SYNC-IOSMAC-084 | Files | Message audio attachment materializes in its chat | Both | Either | Peer | P1 | Pro | Not Started | The owning conversation and message have stable synced IDs. | Attach a supported audio; sync in both directions. | Attachment waits for its message if necessary, appears once and opens from the owning chat.
SYNC-IOSMAC-085 | Files UI | Sent and Received filters are directionally correct | Both | Either | Peer | P0 | Pro | Not Started | At least one sent and one received file exist. | Select All, Sent and Received. | Counts and rows reflect local direction, not origin alone.
SYNC-IOSMAC-086 | Files UI | Origin-device filter is separate from direction | Both | Either | Peer | P1 | Pro | Not Started | Files from both devices exist. | Filter by origin and combine with Sent/Received. | Origin counts and file rows are correct without conflating sender and receiver.
SYNC-IOSMAC-087 | Files UI | Grid mode shows dense cards without previews | Both | Either | Peer | P1 | Pro | Not Started | Synced Files contains several items. | Select Grid and resize the macOS window. | Cards keep a stable width; larger windows fit more columns; actions remain accessible.
SYNC-IOSMAC-088 | Files UI | Preview mode uses orientation-aware image fitting | Both | Either | Peer | P1 | Pro | Not Started | Landscape and portrait images exist. | Select Preview. | Landscape uses the shared appropriate fit; portrait remains fully legible without distortion.
SYNC-IOSMAC-089 | Files UI | One-click in-app preview opens the selected file | Both | Either | Peer | P0 | Pro | Not Started | A previewable image, text or PDF is materialized. | Click the card/preview. | An in-app preview opens with correct aspect and a working Open action.
SYNC-IOSMAC-090 | Files UI | Open, Reveal/Share, Save As and Delete actions work | Both | Either | Peer | P0 | Pro | Not Started | A materialized file exists. | Exercise every action supported on each platform. | Actions target the correct local file; unsupported actions are not offered.
SYNC-IOSMAC-091 | Files UI | Deleting a sync-owned file converges | Both | Either | Peer | P0 | Pro | Not Started | A screenshot/download/shared file exists on both devices. | Delete it on one device; reconnect/restart. | The tombstone removes the sync-owned record and bytes without deleting Gallery/chat-owned content incorrectly.
SYNC-IOSMAC-092 | Files UI | Completed files and history survive restart | Both | Either | Peer | P0 | Pro | Not Started | Completed file records exist. | Restart both apps and reopen Files/Activity. | Durable Files and completed history remain; unavailable local bytes are labelled truthfully.
SYNC-IOSMAC-093 | Activity & notifications | Completed activity hides its progress bar | Both | Either | Peer | P1 | Pro | Not Started | A transfer has completed. | Open Activity immediately after completion. | Completed state and actions are shown without a redundant 100% progress bar.
SYNC-IOSMAC-094 | Activity & notifications | Completed activity auto-archives after five seconds | Both | Either | Peer | P1 | Pro | Not Started | A transfer completes while Activity is visible. | Observe All and Completed. | The completion confirmation leaves current activity after five seconds but stays in durable Completed history.
SYNC-IOSMAC-095 | Activity & notifications | Transfer completion creates sender and receiver feedback | Both | Either | Peer | P0 | Pro | Not Started | A file transfer completes. | Inspect notifications on both devices. | Sender sees File sent; receiver sees File received, with immutable origin and Open/View.
SYNC-IOSMAC-096 | Activity & notifications | Unread badge counts only unread actionable/completion items | Both | Either | Peer | P0 | Pro | Not Started | Notifications contain read and unread items. | Read/dismiss items and return to the navigation badge. | Badge shows 1–9 and 9+ based only on unread notifications.
SYNC-IOSMAC-097 | Activity & notifications | Approvals are newest-first and actionable | Both | Either | Peer | P0 | Pro | Not Started | Several Ask items exist. | Open Notifications; approve/reject newer and older items. | Newest appears first; ✓ and × affect exactly the selected file and named destination.
SYNC-IOSMAC-098 | Activity & notifications | Notification Open/View navigates to the correct file | Both | Either | Peer | P1 | Pro | Not Started | A completion notification references an available file. | Press Open or View. | App navigates to the file destination or opens the preview; unavailable content is explained.
SYNC-IOSMAC-099 | Activity & notifications | Dismiss removes only notification state | Both | Either | Peer | P1 | Pro | Not Started | A completion notification and durable file exist. | Dismiss the notification. | Notification disappears while the durable file remains in Synced Files.
SYNC-IOSMAC-100 | Persistence & conflicts | State and queues survive simultaneous app restarts | Both | Either | Peer | P0 | Pro | Not Started | Chats, files, pairings and queued work exist. | Restart both apps. | Pairing, policy, queue, provenance and materialized records are preserved.
SYNC-IOSMAC-101 | Persistence & conflicts | Received state does not echo back | Both | Either | Peer | P0 | Pro | Not Started | A new record is created on one device. | Let it sync and inspect tracked changes/activity. | The receiver materializes with sync origin and does not rebroadcast a duplicate mutation.
SYNC-IOSMAC-102 | Persistence & conflicts | Latest concurrent update wins deterministically | Both | Either | Peer | P1 | Pro | Not Started | Both devices can edit the same portable record while disconnected. | Make conflicting edits; reconnect. | Both devices converge to one deterministic latest winner with preserved origin provenance.
SYNC-IOSMAC-103 | Persistence & conflicts | A tombstone prevents stale resurrection | Both | Either | Peer | P0 | Pro | Not Started | A record exists on both devices; one device can be offline. | Delete while the peer is offline; reconnect. | The deleted record stays deleted and staged content is cleaned.
SYNC-IOSMAC-104 | Persistence & conflicts | Rematerialization restores ephemeral coordinators after restart | Both | Either | Peer | P1 | Pro | Not Started | Persisted winning state and staged work exist. | Restart before materialization completes. | Persisted winners replay into coordinators and pending work completes without anti-entropy loss.
SYNC-IOSMAC-105 | Desktop capture | Replay capture toggle updates the menu-bar capture state immediately | macOS local | macOS | macOS | P0 | Pro | Verified by User | Replay screen and menu-bar item are available. | Toggle Disable/Enable capture in Replay and inspect the menu bar. | Menu label/action changes immediately in both directions. |  | User manually verified after Pro commit 58733e0.
SYNC-IOSMAC-106 | Desktop capture | Cold start with capture Off requests no Screen Recording access | macOS local | macOS | macOS | P0 | Pro | Not Started | Fresh or permission-reset test profile with capture Off. | Launch the app without enabling capture. | No Screen Recording boundary call or system prompt occurs.
SYNC-IOSMAC-107 | Desktop capture | Explicit capture enablement handles denial and relaunch | macOS local | macOS | macOS | P1 | Pro | Not Started | Capture is Off and Screen Recording is not granted. | Enable from Setup; deny; recover; grant; relaunch. | Denial leaves capture Off with recovery UI; grant reports Restart required and succeeds after relaunch.
SYNC-IOSMAC-108 | Navigation | Cmd+[ and Cmd+] traverse major screens and internal Sync tabs | macOS local | macOS | macOS | P1 | Pro | Not Started | Core navigation history is implemented for major views and Sync tab subroutes. | Navigate through major screens and Devices/Sharing/Activity/Files; use Cmd+[ and Cmd+]. | Every screen/tab transition participates in backward/forward history. |  | Implementation is in src/renderer/src/App.tsx; manual verification remains.

## Environment
Physical Test Environment
Field | iOS value | macOS value | Required? | Verified? | Notes
Device model |  |  | Yes
OS version |  |  | Yes
App version / commit |  |  | Yes
Build type |  |  | Yes |  | Debug, dev or signed packaged build
Device ID / name |  |  | Yes
Pairing code before test |  |  | Yes |  | Do not place trust secrets here
Paired membership count |  |  | Yes |  | Expected maximum is 5 total devices
Wi-Fi network |  |  | For LAN tests |  | Record SSID or isolated test network
Cable connected |  |  | Route-dependent |  | Record before each route test
Nearby available |  |  | Route-dependent |  | Record factual adapter health
Local folder permissions |  |  | File tests |  | Record granted/denied and selected folder
Test start time |  |  | Yes |  | Use yyyy-mm-dd hh:mm

## Run Log
Manual Test Run Log
Add one row for every execution or retest. Keep Test ID aligned with the Test Matrix.
Run date | Tester | Test ID | Direction | Result | Build / commit | Evidence path | Bug ID | Notes